## Slide 1: NGRER SAS to R Transition
Methodology/Algorithm Validation; Code Transition, Modernization, & Development.
Information Current as of:
2025-11-17
Reported by:
Joe Pruitt, ORSA/CTR

## Slide 2: NGRER SAS Optimization System - Current
Bottom Line Up Front
  Optimization is the RIGHT approach for NGRER's complex resource allocation problem
  R migration is feasible within DoD constraints
  Significant long-term benefits justify the migration investment
Next Step: Approve Phase 1 proof-of-concept to validate approach with single-component test case

## Slide 3: NGRER SAS Optimization System - Current
The National Guard and Reserve Equipment Report (NGRER) is a congressionally mandated report that optimally allocates military equipment across Army components to minimize shortfalls and ensure readiness.
NGRER Optimization System Problem Statement
Core Challenge: HQDA-G8 is divesting SAS licenses, forcing migration of the critical National Guard and Reserve Equipment Report (NGRER) optimization system—comprising 22 interconnected SAS scripts that implement sophisticated mixed-integer linear programming models to allocate billions of dollars in military equipment across Army components for Congressional reporting compliance.
Immediate Risk: Without successful migration to R, the Army risks losing analytical capability for the congressionally mandated NGRER that optimizes equipment distribution across Active Component, Army National Guard, Army Reserve, and Army Prepositioned Stocks, potentially compromising statutory reporting requirements and equipment readiness assessments.

## Slide 4: NGRER SAS Optimization System - Current
Current System Architecture
  Core Components
  Data Processing - SACS requirements, LDAC inventory, procurement plans
  Clustering - Graph-based problem decomposition using substitution relationships
  Optimization - MILP model with 100,000+ variables, 5% optimality gap
  Reporting - Automated Excel deliverables for Congressional submission
  Two Scenarios
  GTW (Go-To-War): Allows equipment substitutions
  OSD: No substitutions (conservative baseline)
Mathematical Model
  Objective Function: Minimize: 10¹⁰ × ERC-P Shortages + 500 × ERC-A Shortages + Transfer Penalties
  Key Constraints
    Inventory conservation across components (AC, ARNG, USAR, APS)
    Equipment substitution rules (higher modernization levels only)
    DARPL unit priorities

## Slide 5: NGRER SAS Optimization System - Current
Migration Strategy
Recommended Approach: R
Why R? Built-in optimization solvers work in DoD Nexus environment
Timeline: 22-24 weeks for complete migration
Key Benefits: Better maintainability, modern interfaces, cloud deployment
Major Phases
Foundation (Weeks 1-4): Environment setup, data mapping
Data Processing (Weeks 5-8): Core data transformation
Optimization (Weeks 11-14): MILP model implementation
Integration (Weeks 19-22): End-to-end system testing
Value Proposition
Technical Benefits
50-80% performance improvement with modern solvers
Enhanced maintainability with modular R architecture
Better scalability for growing data volumes
Operational Benefits
Maintains analytical rigor required for Congressional reporting
Preserves existing mathematical models that are proven effective
Enables future enhancements (real-time optimization, interactive dashboards)

## Slide 6: NGRER SAS to R – POAM (Overview)
Task: Migrate the National Guard and Reserve Equipment Report (NGRER) optimization system from legacy SAS to R programming environment while preserving all mathematical optimization capabilities and statutory reporting compliance.
Purpose: Modernize the Army's equipment allocation analytical capabilities to ensure continued optimal resource distribution across Active Component, Army National Guard, and Army Reserve formations for Congressional readiness reporting.
Completed Work:
Week 1: Verify DoD Nexus R package availability
Installed and tested: ‘lpSolve`, `ROI`, `Rglpk`, `dplyr`, `data.table`, `readxl`, `openxlsx`, `igraph’
All relevant libraries available in cProbe Workbench and Rstudio Desktop
Ongoing Work:
Week 2: Complete data source inventory
Map all 8 required input files to R data structures
Document data transformations and business rules
Create data dictionary with field mappings
Establish data quality validation rules
Future Work:
Weeks 3-4: Define R project structure and standards
Establish coding conventions and documentation standards
Design modular architecture with clear interfaces
Create logging and error handling framework
Set up version control and testing infrastructure
Project Phases:
Phase 1: Foundation and Infrastructure (Weeks 1-4)
Phase 2: Core Data Processing Migration (Weeks 5-8)
Phase 2.5: Advanced Optimization Features (Weeks 9-12)
Phase 3: Clustering and Problem Decomposition (Weeks 13-14)
Phase 4: Core Optimization Engine (Weeks 15-18)
Phase 5: Reporting and Analysis (Weeks 19-22)
Phase 6: Integration and System Testing (Weeks 23-26)
Follow-On Phase: Additional Optimization and Reporting Excursions; Automation (Weeks 27+)
R
2

## Slide 7: NGRER SAS to R – POAM (Overview)
Follow-On Phase:
Additional Optimization and Reporting Excursions; Automation (Weeks 27+)
Phase 6: Integration and System Testing (Weeks 23-26)
Phase 5: Reporting and Analysis (Weeks 19-22)
Phase 4: Core Optimization Engine (Weeks 15-18)
Phase 3: Clustering and Problem Decomposition (Weeks 13-14)
Phase 2.5: Advanced Optimization Features (Weeks 9-12)
Milestone 6.1: End-to-End Integration
Milestone 6.2: Performance Optimization
Milestone 6.3: Comprehensive Validation
Milestone 5.1: Core Report Generation
Milestone 5.2: Summary Reports
Milestone 5.3: Cost Analysis
Milestone 5.4: Excel Output Integration
Milestone 4.1: Base Optimization Model
Milestone 4.2: Advanced Optimization Features
Milestone 4.3: No-Substitution Variant
Milestone 4.4: Solver Integration and Testing
Milestone 3.1: Graph-Based Clustering
Milestone 3.2: Cluster Processing Framework
Milestone 2.1: Index Set Generation
Milestone 2.2: Input Data Processing
Milestone 2.3: Substitution Rules Processing
Milestone 2.4: LMI Transfer Integration
Phase 2: Core Data Processing Migration (Weeks 5-8)
Milestone 1.1: Environment Setup and Package Verification
Milestone 1.2: Data Source Analysis and Mapping
Milestone 1.3: Core Architecture Design
Phase 1: Foundation and Infrastructure (Weeks 1-4)
Begin Date: 2025-11-17
Milestone 2.5.1: Stochastic Programming Implementation
Milestone 2.5.2: Multi-Objective Optimization
Milestone 2.5.3: Dynamic Programming Integration
New Optimization Goals
New Reporting Products
New Visualization Products/ Dashboards
Data Pipeline Automation
R
2

## Slide 8: NGRER SAS to R – POAM (Phase 1)
Phase 1: Foundation and Infrastructure (Weeks 1-4)
Milestone 1.1: Environment Setup and Package Verification
Milestone 1.2: Data Source Analysis and Mapping
Milestone 1.3: Core Architecture Design
Week 1: Verify DoD Nexus R package availability
Test `lpSolve`, `ROI`, `Rglpk` installation and functionality
Confirm `dplyr`, `data.table`, `readxl`, `openxlsx` availability
Validate `igraph` for clustering algorithms
Document any missing packages requiring approval
Week 2: Complete data source inventory
Map all 8 required input files to R data structures
Document data transformations and business rules
Create data dictionary with field mappings
Establish data quality validation rules
Weeks 3-4: Define R project structure and standards
Establish coding conventions and documentation standards
Design modular architecture with clear interfaces
Create logging and error handling framework
Set up version control and testing infrastructure
Begin Date: 2025-11-17
R
2

## Slide 9: NGRER SAS to R – POAM (Phase 2)
Milestone 2.1: Index Set Generation
Milestone 2.2: Input Data Processing
Milestone 2.3: Substitution Rules Processing
Phase 2: Core Data Processing Migration (Weeks 5-8)
Milestone 2.4: LMI Transfer Integration
Week 5: Migrate `MAKE_INDEX_SETS_v2.sas`
Create LIN, unit, component, and ERC master lists
Implement data standardization functions
Validate against existing SAS outputs
Week 6: Migrate `generate_opt_model_inputs.sas`
SACS requirements processing
LDAC inventory integration
DARPL priority assignment
FDIIS-LQA procurement data handling
Week 7: Implement substitution rule logic
SB 700-20 Appendix H processing
LMDB substitution rule integration
Source prioritization (1-2 vs 3-9)
Modernization level validation
Week 8: Equipment transfer processing
DST transfer data processing
Unit-level transfer calculations
Component transfer validation

## Slide 10: NGRER SAS to R – POAM (Phase 2.5)
Phase 2.5: Advanced Optimization Features (Weeks 9-12)
Milestone 2.5.1: Stochastic Programming Implementation
Milestone 2.5.2: Multi-Objective Optimization
Milestone 2.5.3: Dynamic Programming Integration
Week 9 : Implement uncertainty modeling for demand forecasting
Data Sources : Historical variance data, forecast confidence intervals
R Implementation: Stochastic programming with scenario generation
Week 10 : Implement Pareto-optimal trade-off analysis
Objectives :
Cost minimization vs. readiness maximization vs. modernization priorities
Multi-criteria optimization
Week 11 : Equipment lifecycle optimization across multiple periods
Week 12 : Replacement timing optimization

## Slide 11: NGRER SAS to R – POAM (Phase 3)
Phase 3: Clustering and Problem Decomposition (Weeks 13-14)
Milestone 3.1: Graph-Based Clustering
Milestone 3.2: Cluster Processing Framework
Week 13: Migrate `Make_Clusters_Optmodel_with_LINs.txt`
Implement breadth-first search clustering
Connected components analysis using `igraph`
Cluster validation and size optimization
Week 14: Migrate `generate_clusters.sas`
Component-wise vs. integrated processing logic
Index set creation for each cluster
Transfer rule validation framework

## Slide 12: NGRER SAS to R – POAM (Phase 4)
Milestone 4.1: Base Optimization Model
Milestone 4.2: Advanced Optimization Features
Milestone 4.3: No-Substitution Variant
Phase 4: Core Optimization Engine (Weeks 15-18)
Milestone 4.4: Solver Integration and Testing
Week 15: Migrate core MILP formulation from `model_optimization.sas`
Decision variable definitions
Constraint matrix construction
Objective function implementation using `lpSolve`
Week 16: Implement substitution and transfer logic
ERC P/A assignment variables
Substitution assignment constraints
Intercomponent transfer variables
DARPL priority weighting
Week 17: Migrate `model_optimization_nosubs.sas`
OSD scenario implementation
Simplified constraint structure
Performance optimization
Week 18: Optimize solver performance
Test `lpSolve` scalability limits
Implement solution validation
Error handling and infeasibility detection

## Slide 13: NGRER SAS to R – POAM (Phase 5)
Milestone 5.1: Core Report Generation
Milestone 5.2: Summary Reports
Milestone 5.3: Cost Analysis
Phase 5: Reporting and Analysis (Weeks 19-22)
Milestone 5.4: Excel Output Integration
Week 19: Migrate `generate_reports_NGRER_calc.sas` and `generate_reports_NGRER_new.sas`
Equipment on-hand by modernization level
Shortage and excess calculations
Substitution assignment reporting
Week 20: Migrate `NGRER_Summary_reports.txt`
Executive summary charts
Component-level aggregations
Top shortage analysis
Major capability analysis
Week 21: Migrate `calc_slide 4_5.txt`
Unit cost integration
Shortage cost calculations
Equipment value analysis
Week 22: Migrate `write_ngrer_reports.txt`
Excel template population using `openxlsx`
Replace DDE with modern R Excel interfaces
Automated chart and table generation

## Slide 14: NGRER SAS to R – POAM (Phase 6)
Phase 6: Integration and System Testing (Weeks 23-26)
Milestone 6.1: End-to-End Integration
Milestone 6.2: Performance Optimization
Milestone 6.3: Comprehensive Validation
Week 23: Complete system integration
Main orchestration script development
Parameter configuration system
Log file generation and monitoring
Week 24: System performance tuning
Memory usage optimization
Processing time improvements
Parallel processing where applicable
Weeks 25-26: Full system validation
Historical data validation
Cross-reference with SAS outputs
User acceptance testing

## Slide 15: NGRER SAS to R – POAM (Potential Follow-on)
Follow-On Phase:
Additional Optimization and Reporting Excursions; Automation (Weeks 27+)
New Optimization Goals
New Reporting Products
New Visualization Products/ Dashboards
Data Pipeline Automation

## Slide 16: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (1 of 6)
Data Standardization Rules
Field Naming Conventions:
Unit Identifiers: `uic` → `units`
Components: `compo` → `compos`
Line Item Numbers: `lin` → `lins`
Equipment Readiness Codes: `erc` → `ercs`
Requirements: `req` → `reqd`
Quantities: `qty` → `inv`
Fiscal Years: `FY` → `dates`
Component Code Standardization:
`1` = Active Component (AC)
`2` = Army National Guard (ARNG)
`3` = Army Reserve (USAR)
`6` = Army Prepositioned Stocks (APS)
Data Quality Controls:
Remove TYPCO 3 (TDA) units: `if typco ne '3'`
Positive requirements only: `if rqeqp > 0`
Valid LIN format: 6-character alphanumeric
Equipment condition filtering: Remove obsolete (LCC S,O) and unserviceable (H,P,S)
Output Datasets Generated
idm_i.requirements Standardized equipment requirements by unit/LIN/ERC/year
idm_i.inventory Standardized equipment inventory by unit/LIN/component
idm_i.procurements Standardized procurement plans by LIN/component/year
idm_i.darpl Unit priority rankings by fiscal year
idm_i.sub_rules Equipment substitution relationships with source priorities
idm_i.lins Master LIN index with modernization levels
idm_i.units Master unit index
idm_i.compos Master component index
idm_i.ercs Master ERC index
idm_i.LMI_XFER_ADD/REMOVE Equipment transfer plans
Summary

## Slide 17: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (2 of 6)
Input Data Files:
cla_eqpdet_roll[date].txt Equipment Details
cla_header_roll[date].txt Equipment Headers
Processing Operations:
dates = FY; Convert fiscal year to dates format
rename uic = units; Standardize unit identifier
rename compo = compos; Standardize component code
rename lin = lins; Standardize line-item number
rename erc = ercs; Standardize equipment readiness code
rename req = reqd; Standardize requirement quantity
drop FY typco auth; Remove unnecessary fields
Transformation Operations:
Fiscal year date conversion: `dates = FY`
Equipment filtering: Only TYPCO 1 (MTO&E) and 2 (Augmentation TDA) retained
ERC consolidation: ERCs B and C mapped to A (`if erc in ("B","C") then erc = "A"`)

## Slide 18: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (3 of 6)
Input Data Files:
AE2S_LIN_DATA_G8_NIIN_File_[date].xlsx - 3 sheets Primary Inventory
compo.Initial_inventory → compo.inventory_by_uic Processing through
Processing Operations:
dates = &current_fy; Assign current fiscal year
rename compo = compos; Standardize component field
rename lin = lins; Standardize LIN field
rename uic = units; Standardize unit field
rename qty = inv; Standardize quantity field
Transformation Operations:
if lcc in &obsolete then output obsolete; Obsolete equipment
if condition_code in &unserviceable then output unserviceables; Unserviceable
else output LIN_INV; Usable inventory

## Slide 19: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (4 of 6)
Input Data Files:
AE2S_CURRENT_POSITION_[date].xlsx - Sheet: "AE2S_CURRENT_POSITION"
Processing Operations:
compo3=put(compo,1.); Convert component to character
rename FY = dates; Standardize fiscal year field
rename compo = compos; Standardize component field
rename lin = lins; Standardize LIN field
Transformation Operations:
sum(Amount) as Qty Sum quantities by LIN/Component/Year
Input Data Files:
CUI_[date]_RPT_DARPL_RELEASE_FY[year].xlsx
Processing Operations:
dates = FY; Convert fiscal year
rename uic = units; Standardize unit field
rename compo = compos; Standardize component field
drop FY; Remove original FY field

## Slide 20: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (5 of 6)
Input Data Files:
LINS_ACTIVE_[date].xlsx - Sheet: "LINS_Active"
Processing Operations:
set lmdb.lins; Use processed LIN list
Input Data Files:
SB_700_20_APPENDIX_H_[date].xlsx Army regulation substitutions
Processing Operations:
rename lin = lins; Standardize LIN field
rename sublin = sublins; Standardize substitute LIN field
sources = substrn(source,1,1); Extract source priority
drop run_id start_dt source; Remove metadata fields
rename sources = source; Rename for consistency

## Slide 21: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.1: Master Data Sources Integration (6 of 6)
Input Data Files:
LMI_DST_PSDs [date].xlsx - Planned equipment transfers
Processing Operations:
data idm_i.LMI_XFER_REMOVE; Process transfer removals
set compo.LMI_XFER_REMOVE; Process transfer removals
data idm_i.LMI_XFER_ADD; Process transfer additions
set compo.LMI_XFER_ADD; Process transfer additions
Processing Operations:
create table lins as Create comprehensive LIN index
  select distinct lin as LINs; from lmdb.lmdb_&lmdb_month Primary LIN source
  select distinct lin as LINs; from lmdb.subrules_final Substitution LINs
  select distinct lin as LINs; from compo.procurements Procurement LINs
  select distinct lin as LINs; from compo.inventory_by_uic Inventory LINs
  select distinct lin as LINs; from compo.all_lin_reqs; Requirement LINs
create table idm_i.units as Create units index
  select distinct uic as units; from compo.units;
create table idm_i.compos as Create components index
  select distinct compo as compos; from compo.all_lin_reqs;
create table idm_i.ercs as Create ERCs index
  select distinct erc as ercs; from compo.all_lin_reqs;

## Slide 22: NGRER SAS Optimization Algorithm Walkthrough
Step 1: Data Ingestion and Preprocessing Architecture
1.2 Index Set Generation (Source: MAKE_INDEX_SETS_v2.txt)
Hierarchical UNION operations:
create table lins as
select distinct lin as LINs; from lmdb.lmdb_&lmdb_month LIN Management Database Primary
Union; select distinct lin as LINs; from lmdb.subrules_final Substitution Rules Secondary
Union; select distinct lin as LINs; from compo.procurements Procurement Plans Tertiary
Union; select distinct lin as LINs; from compo.inventory_by_uic Inventory Quaternary
Union; select distinct lin as LINs; from compo.all_lin_reqs; Requirements Base Set
Mathematical Representation:
L = {l₁, l₂, ..., l_n} : Set of Line Item Numbers (LINs)
U = {u₁, u₂, ..., u_m} : Set of Unit Identification Codes (UICs)
C = {1, 2, 3, 6} : Set of Components (AC, ARNG, USAR, APS)
D = {d₁, d₂, ..., d_t} : Set of Fiscal Years
E = {P, A} : Set of Equipment Readiness Codes

## Slide 23: NGRER SAS Optimization Algorithm Walkthrough
Step 2: Graph-Based Clustering for Problem Decomposition
2.1 Substitution Graph Construction:
The system creates a bidirectional graph G = (V, E) where:
V = Set of LINs
E = Set of substitution relationships Bidirectional Edges
2.2 Connected Components Algorithm:
Breadth-First Search Implementation:
create table arcs_2 as
select (a.lins, b.nodes) as sublins from arcs_1 as a
inner join nodes as b on a.sublins = b.lins;
insert into arcs
select (sublins as lins, lins as sublins) from arcs_2;