Comprehensive SAS to R Migration Plan for NGRER Optimization System

Executive Summary

This plan outlines the complete migration of the National Guard and Reserve Equipment Report (NGRER) optimization system from SAS to R. The system consists of 22 interconnected SAS scripts implementing a mixed-integer linear programming (MILP) model for military equipment allocation across components (Active, ARNG, USAR, APS) with complex substitution rules and multi-year forecasting.

NGRER Optimization System Migration Project: Problem Statement

Core Problem

The U.S. Army Headquarters, Department of the Army G-8 (Resource Management) faces a critical technology transition challenge that threatens the continuity of the National Guard and Reserve Equipment Report (NGRER), a congressionally mandated analytical capability responsible for optimizing billions of dollars in military equipment allocation decisions across Army components.

Immediate Drivers

Enterprise Software Divestiture

HQDA-G8 is divesting SAS licenses as part of Army-wide cost reduction and technology modernization initiatives, creating an urgent need to migrate mission-critical analytical capabilities to alternative platforms before license expiration compromises operational readiness reporting to Congress.

Technical Debt and System Complexity

The current NGRER optimization system consists of 22 interconnected SAS scripts implementing sophisticated mixed-integer linear programming (MILP) models that allocate equipment across Active Component, Army National Guard, Army Reserve, and Army Prepositioned Stock formations. This complex system has evolved over multiple years without comprehensive modernization, creating:

- Scalability limitations preventing efficient processing of growing data volumes and analytical requirements

- Maintainability challenges due to legacy code architecture and limited documentation

- Performance constraints that extend processing time beyond acceptable operational windows

- Technology obsolescence incompatible with modern Army Resource Cloud infrastructure

Mission Impact

Congressional Reporting Risk

The NGRER directly supports statutory requirements under Title 10, Section 10541, providing Congress with critical assessments of National Guard and Reserve equipment readiness. System failure or degradation would compromise the Army's ability to:

- Document equipment shortfalls affecting reserve component readiness

- Justify procurement and funding requests totaling billions of dollars annually

- Demonstrate compliance with federal equipment allocation mandates

- Support strategic decision-making for force structure and modernization

Operational Consequences

Without successful migration to a modern platform, the Army risks:

- Loss of analytical capability during the critical transition period

- Degraded accuracy in equipment allocation decisions affecting unit readiness

- Compliance failures with congressional reporting requirements

- Inefficient resource utilization due to suboptimal equipment distribution algorithms

Technical Challenges

The migration must preserve sophisticated mathematical optimization capabilities while addressing:

- Complex algorithm preservation ensuring no degradation in optimization quality

- Data integration complexity across multiple authoritative Army systems

- Performance requirements maintaining or improving current processing capabilities

- Validation and verification ensuring mathematical accuracy and business rule compliance

Task Statement

The U.S. Army G-8 (Resource Management) is directed to migrate the National Guard and Reserve Equipment Report (NGRER) optimization system from the legacy SAS platform to a modern R programming environment. This migration will preserve all existing mathematical optimization capabilities while enhancing system performance, maintainability, and analytical flexibility. The project team will analyze 22 interconnected SAS scripts comprising a sophisticated mixed-integer linear programming model that allocates military equipment across Active Component, Army National Guard, Army Reserve, and Army Prepositioned Stock formations. The migration must maintain full compliance with Title 10, Section 10541 statutory reporting requirements while providing enhanced analytical capabilities for Congressional equipment readiness assessments.

Purpose Statement

The NGRER optimization system serves as the Army's primary analytical tool for equipment allocation and readiness reporting to Congress, processing billions of dollars in military equipment investments across multiple components and fiscal years. The current SAS-based system, while mathematically robust, presents operational challenges including limited scalability, aging technology infrastructure, and restricted analytical flexibility within the Army Resource Cloud environment.

This migration to R will modernize the Army's equipment optimization capabilities by leveraging contemporary programming languages and enhanced solver technologies while preserving the sophisticated mathematical models that ensure optimal equipment distribution based on unit priorities, modernization levels, and substitution rules. The upgraded system will continue to support critical statutory requirements including equipment shortfall identification, procurement planning, cost analysis, and interoperability assessments that directly inform Congressional funding decisions and Army readiness posture.

For technical audiences, this project represents a comprehensive system reengineering effort involving complex optimization algorithms, multi-dimensional data processing, and statistical modeling. For non-technical stakeholders, this modernization effort ensures the Army maintains cutting-edge analytical capabilities to optimize equipment distribution and provide accurate readiness assessments to Congress and senior leadership.

The successful completion of this migration will enhance the Army's ability to efficiently allocate equipment resources, reduce analytical processing time, and provide more responsive support to strategic decision-making processes affecting National Guard and Reserve readiness.

Phase-Based Migration Strategy

- Phase 1: Foundation and Infrastructure (Weeks 1-4)

  - Milestone 1.1: Environment Setup and Package Verification

    - Week 1: Verify DoD Nexus R package availability

    - Test `lpSolve`, `ROI`, `Rglpk` installation and functionality

    - Confirm `dplyr`, `data.table`, `readxl`, `openxlsx` availability

    - Validate `igraph` for clustering algorithms

    - Document any missing packages requiring approval

  - Milestone 1.2: Data Source Analysis and Mapping

    - Week 2: Complete data source inventory

    - Map all 8 required input files to R data structures

    - Document data transformations and business rules

    - Create data dictionary with field mappings

    - Establish data quality validation rules

  - Milestone 1.3: Core Architecture Design

    - Weeks 3-4: Define R project structure and standards

    - Establish coding conventions and documentation standards

    - Design modular architecture with clear interfaces

    - Create logging and error handling framework

    - Set up version control and testing infrastructure

- Phase 2: Core Data Processing Migration (Weeks 5-8)

  - Milestone 2.1: Index Set Generation

    - Week 5: Migrate `MAKE_INDEX_SETS_v2.sas`

    - Create LIN, unit, component, and ERC master lists

    - Implement data standardization functions

    - Validate against existing SAS outputs

  - Milestone 2.2: Input Data Processing

    - Week 6: Migrate `generate_opt_model_inputs.sas`

    - SACS requirements processing

    - LDAC inventory integration

    - DARPL priority assignment

    - FDIIS-LQA procurement data handling

  - Milestone 2.3: Substitution Rules Processing

    - Week 7: Implement substitution rule logic

    - SB 700-20 Appendix H processing

    - LMDB substitution rule integration

    - Source prioritization (1-2 vs 3-9)

    - Modernization level validation

  - Milestone 2.4: LMI Transfer Integration

    - Week 8: Equipment transfer processing

    - DST transfer data processing

    - Unit-level transfer calculations

    - Component transfer validation

- Phase 2.5: Advanced Optimization Features (Weeks 9-12)

  - Milestone 2.5.1: Stochastic Programming Implementation

    - Week 9 : Implement uncertainty modeling for demand forecasting

    - Data Sources : Historical variance data, forecast confidence intervals

    - R Implementation :

# Stochastic programming with scenario generation

library(ROI)

library(rstochopt)

implement_stochastic_demand <- function(base_requirements, variance_data) {

# Generate scenarios for uncertain demand

scenarios <- generate_demand_scenarios(base_requirements, variance_data)

# Multi-stage optimization with recourse decisions

stochastic_model <- create_stochastic_milp(scenarios)

return(stochastic_model)

}

  - Milestone 2.5.2: Multi-Objective Optimization

    - Week 10 : Implement Pareto-optimal trade-off analysis

    - Objectives : Cost minimization vs. readiness maximization vs. modernization priorities

library(mco)  # Multi-criteria optimization

multi_objective_ngrer <- function(equipment_data) {

objectives <- list(

minimize_cost = cost_function,

maximize_readiness = readiness_function,

maximize_modernization = modernization_function

)

pareto_solutions <- nsga2(objectives, equipment_data)

return(pareto_solutions)

}

  - Milestone 2.5.3: Dynamic Programming Integration

    - Week 11 : Equipment lifecycle optimization across multiple periods

    - Week 12 : Replacement timing optimization

implement_dynamic_programming <- function(equipment_lifecycle_data) {

# Multi-period equipment replacement decisions

dp_stages <- setup_lifecycle_stages(equipment_lifecycle_data)

optimal_policy <- backward_induction(dp_stages)

return(optimal_policy)

}

- Phase 3: Clustering and Problem Decomposition (Weeks 13-14)

  - Milestone 3.1: Graph-Based Clustering

    - Week 13: Migrate `Make_Clusters_Optmodel_with_LINs.txt`

    - Implement breadth-first search clustering

    - Connected components analysis using `igraph`

    - Cluster validation and size optimization

  - Milestone 3.2: Cluster Processing Framework

    - Week 14: Migrate `generate_clusters.sas`

    - Component-wise vs. integrated processing logic

    - Index set creation for each cluster

    - Transfer rule validation framework

- Phase 4: Core Optimization Engine (Weeks 15-18)

  - Milestone 4.1: Base Optimization Model

    - Week 15: Migrate core MILP formulation from `model_optimization.sas`

    - Decision variable definitions

    - Constraint matrix construction

    - Objective function implementation using `lpSolve`

  - Milestone 4.2: Advanced Optimization Features

    - Week 16: Implement substitution and transfer logic

    - ERC P/A assignment variables

    - Substitution assignment constraints

    - Intercomponent transfer variables

    - DARPL priority weighting

  - Milestone 4.3: No-Substitution Variant

    - Week 17: Migrate `model_optimization_nosubs.sas`

    - OSD scenario implementation

    - Simplified constraint structure

    - Performance optimization

  - Milestone 4.4: Solver Integration and Testing

    - Week 18: Optimize solver performance

    - Test `lpSolve` scalability limits

    - Implement solution validation

    - Error handling and infeasibility detection

- Phase 5: Reporting and Analysis (Weeks 19-22)

  - Milestone 5.1: Core Report Generation

    - Week 19: Migrate `generate_reports_NGRER_calc.sas` and `generate_reports_NGRER_new.sas`

    - Equipment on-hand by modernization level

    - Shortage and excess calculations

    - Substitution assignment reporting

  - Milestone 5.2: Summary Reports

    - Week 20: Migrate `NGRER_Summary_reports.txt`

    - Executive summary charts

    - Component-level aggregations

    - Top shortage analysis

    - Major capability analysis

  - Milestone 5.3: Cost Analysis

    - Week 21: Migrate `calc_slide 4_5.txt`

    - Unit cost integration

    - Shortage cost calculations

    - Equipment value analysis

  - Milestone 5.4: Excel Output Integration

    - Week 22: Migrate `write_ngrer_reports.txt`

    - Excel template population using `openxlsx`

    - Replace DDE with modern R Excel interfaces

    - Automated chart and table generation

- Phase 6: Integration and System Testing (Weeks 23-26)

  - Milestone 6.1: End-to-End Integration

    - Week 23: Complete system integration

    - Main orchestration script development

    - Parameter configuration system

    - Log file generation and monitoring

  - Milestone 6.2: Performance Optimization

    - Week 24: System performance tuning

    - Memory usage optimization

    - Processing time improvements

    - Parallel processing where applicable

  - Milestone 6.3: Comprehensive Validation

    - Weeks 25-26: Full system validation

    - Historical data validation

    - Cross-reference with SAS outputs

    - User acceptance testing

Comprehensive Testing Regimen

Unit Testing Framework

Data Processing Tests

# Example test structure

test_that("SACS data processing maintains requirement totals", {

# Test data standardization

# Verify component code mapping

# Validate requirement aggregations

})

test_that("LDAC inventory processing filters correctly", {

# Test condition code filtering

# Verify component mapping

# Check quantity aggregations

})

test_that("Substitution rules implement modernization constraints", {

# Test mod_level >= requirements

# Verify source prioritization

# Check bidirectional relationships

})

Optimization Engine Tests

test_that("MILP model formulation is mathematically correct", {

# Verify constraint matrix dimensions

# Test objective function coefficients

# Validate decision variable bounds

})

test_that("Optimization results satisfy all constraints", {

# Test inventory conservation

# Verify requirement satisfaction

# Check substitution rule compliance

})

Integration Testing

End-to-End Data Flow Tests

- Test 1: Historical FY24 data processing

  - Input: Complete FY24 dataset

  - Expected: Exact match with SAS FY24 results

  - Tolerance: <0.1% variance in equipment assignments

- Test 2: Component-specific processing

  - Input: Single component (ARNG) data

  - Expected: Matches SAS single-component run

  - Validation: Assignment totals, shortage calculations

- Test 3: Substitution scenarios

  - Input: Data with known substitution opportunities

  - Expected: Optimal substitution assignments

  - Validation: Cost minimization verification

Performance Testing

Scalability Tests

- Small Dataset: 100 LINs, 50 units Target: <5 minutes

- Medium Dataset: 1,000 LINs, 500 units Target: <30 minutes

- Full Dataset: 2,500+ LINs, 2,000+ units Target: <4 hours

Memory Usage Tests

- Monitor peak memory usage during optimization

- Test memory cleanup between components

- Validate no memory leaks in iterative processing

Validation Testing

Mathematical Model Validation

# Constraint satisfaction validation

validate_constraints <function(solution, inputs) {

# Check inventory conservation

inventory_check <verify_inventory_balance(solution, inputs)

# Check requirement satisfaction

requirement_check <verify_requirement_satisfaction(solution, inputs)

# Check substitution rules

substitution_check <verify_substitution_compliance(solution, inputs)

return(list(

inventory_valid = inventory_check,

requirements_valid = requirement_check,

substitutions_valid = substitution_check

))

}

Business Rule Validation

- DARPL priority implementation

- Component precedence rules (AC → APS → ARNG → USAR)

- Modernization level requirements

- Equipment condition filtering

Recommended File Structure

ngrer_optimization/

├── R/

│   ├── main/

│   │   ├── main_gtw.R                    			# Main GTW scenario orchestration

│   │   ├── main_osd.R                    			# Main OSD scenario orchestration

│   │   └── main_common.R                		# Shared main functions

│   ├── data_processing/

│   │   ├── make_index_sets.R             		# Master index creation

│   │   ├── process_sacs.R                		# SACS requirements processing

│   │   ├── process_ldac.R                		# LDAC inventory processing

│   │   ├── process_darpl.R               		# DARPL priority processing

│   │   ├── process_lqa.R                 		# FDIIS-LQA procurement processing

│   │   ├── process_substitutions.R      		# Substitution rules processing

│   │   └── process_transfers.R           		# LMI transfer processing

│   ├── clustering/

│   │   ├── generate_clusters.R           		# Main clustering logic

│   │   ├── graph_clustering.R            		# Graph-based connected components

│   │   └── cluster_validation.R          		# Cluster quality checks

│   ├── advanced_optimization/

│   │   ├── stochastic_programming.R

│   │   ├── multi_objective_optimization.R

│   │   ├── dynamic_programming.R

│   │   ├── uncertainty_modeling.R

│   │   └── scenario_generation.R

│   ├── modern_solvers/

│   │   ├── commercial_solver_interface.R

│   │   ├── gurobi_implementation.R

│   │   ├── enhanced_lpsolve.R

│   │   └── solver_comparison.R

│   ├── real_time/

│   │   ├── streaming_data_processor.R

│   │   ├── incremental_optimization.R

│   │   └── real_time_dashboard.R

│   ├── machine_learning/

│   │   ├── demand_forecasting.R

│   │   ├── pattern_recognition.R

│   │   ├── predictive_maintenance.R

│   │   └── ml_validation.R

│   ├── optimization/

│   │   ├── model_optimization_gtw.R      		# GTW optimization with substitutions

│   │   ├── model_optimization_osd.R      		# OSD optimization without substitutions

│   │   ├── build_constraints.R           		# Constraint matrix construction

│   │   ├── build_objective.R             		# Objective function construction

│   │   ├── solve_milp.R                  			# MILP solver interface

│   │   ├── validate_solution.R           		# Solution validation

│   │   ├── model_optimization_test.R 		# model_optimization_test.txt equivalent

│   │   └── scenario_comparison.R     		# For GTW vs OSD analysis

│   ├── reporting/

│   │   ├── generate_core_reports.R       		# Basic equipment reports

│   │   ├── generate_summary_reports.R    	# Executive summary reports

│   │   ├── calculate_costs.R             		# Cost analysis calculations

│   │   ├── create_excel_outputs.R        		# Excel report generation

│   │   ├── format_deliverables.R         		# Final deliverable formatting

│   │   ├── generate_substitution_reports.R  	# generate_reports_subs.txt

│   │   └── parity_analysis.R               		# Parity system analysis

│   ├── utilities/

│   │   ├── data_validation.R             		# Data quality checks

│   │   ├── logging.R                     			# Logging framework

│   │   ├── error_handling.R              		# Error handling utilities

│   │   ├── parameter_management.R        		# Configuration management

│   │   ├── file_operations.R             		# File I/O utilities

│   │   ├── substitution_management.R  		# make_sub_ignore_set.txt logic

│   │   ├── parameter_documentation.R  		# set_opt_model_run_params.txt

│   │   └── family_analysis.R         			# lin_family.txt processing

│   └── testing/

│       ├── test_data_processing.R        		# Data processing unit tests

│       ├── test_clustering.R             			# Clustering algorithm tests

│       ├── test_optimization.R           		# Optimization engine tests

│       ├── test_reporting.R              			# Report generation tests

│       └── test_integration.R            			# Integration tests

├── data/

│   ├── input/

│   │   ├── sacs/                         			# SACS equipment requirements

│   │   ├── ldac/                         			# LDAC inventory data

│   │   ├── darpl/                        			# DARPL priority data

│   │   ├── lqa/                         			# FDIIS-LQA procurement data

│   │   ├── lmdb/                         			# LIN Management Database

│   │   ├── substitutions/                			# SB 700-20 substitution rules

│   │   └── transfers/                    			# LMI transfer data

│   ├── processed/

│   │   ├── index_sets/                   			# Master indices

│   │   ├── clusters/                     			# LIN clusters

│   │   └── optimization_inputs/          		# Optimization input datasets

│   └── output/

│       ├── optimization_results/         		# Raw optimization outputs

│       ├── reports/                      			# Generated reports

│       └── deliverables/                 			# Final NGRER deliverables

├── config/

│   ├── parameters_gtw.yaml               		# GTW scenario parameters

│   ├── parameters_osd.yaml               		# OSD scenario parameters

│   ├── data_sources.yaml                 		# Data source configurations

│   └── reporting_config.yaml             		# Report configuration

├── templates/

│   ├── excel/

│   │   └── NGRER_Report_Template.xlsx    	# Excel report template

│   └── markdown/

│       └── summary_report_template.Rmd   	# R Markdown templates

├── logs/                                 			# Execution

Detailed Script List and Dependencies

Core R Scripts (Priority Order)

Tier 1: Foundation Scripts (Weeks 1-4)

R/utilities/

├── data_validation.R             			# Data quality checks

├── logging.R                     				# Logging framework

├── error_handling.R              			# Error handling utilities

├── parameter_management.R        		# Configuration management

├── file_operations.R             			# File I/O utilities

├── substitution_management.R  			# make_sub_ignore_set.txt logic

├── parameter_documentation.R  			# set_opt_model_run_params.txt

└── family_analysis.R         				# lin_family.txt processing

Tier 2: Data Processing Scripts (Weeks 5-8)

R/data_processing/

├── make_index_sets.R           			# Master LIN/unit/component indices

├── process_sacs.R              			# SACS requirements (equipment_details processing)

├── process_ldac.R              			# LDAC inventory (DST_DATA processing)

├── process_darpl.R             			# DARPL priority integration

├── process_lqa.R               				# FDIIS-LQA procurement data

├── process_substitutions.R     			# SB 700-20 substitution rules

└── process_transfers.R         			# LMI transfer data processing

Tier 3: Clustering Scripts (Weeks 9-10)

R/clustering/

├── generate_clusters.R         			# Main clustering orchestration

├── graph_clustering.R          			# Connected components algorithm

└── cluster_validation.R        			# Cluster quality validation

Tier 4: Optimization Scripts (Weeks 11-14)

R/optimization/

├── model_optimization_gtw.R     			# GTW optimization with substitutions

├── model_optimization_osd.R      			# OSD optimization without substitutions

├── build_constraints.R          			# Constraint matrix construction

├── build_objective.R             			# Objective function construction

├── solve_milp.R                  			# MILP solver interface

├── validate_solution.R           			# Solution validation

├── model_optimization_test.R  			# model_optimization_test.txt equivalent

└── scenario_comparison.R     			# For GTW vs OSD analysis

Tier 5: Reporting Scripts (Weeks 15-18)

R/reporting/

├── generate_core_reports.R       			# Basic equipment reports

├── generate_summary_reports.R    		# Executive summary reports

├── calculate_costs.R             			# Cost analysis calculations

├── create_excel_outputs.R        			# Excel report generation

├── format_deliverables.R         			# Final deliverable formatting

├── generate_substitution_reports.R  		# generate_reports_subs.txt

└── parity_analysis.R               			# Parity system analysis

R-Library Dependencies

Core Optimization Libraries

```r

# Mixed-Integer Linear Programming

library(lpSolve)        				# Built-in MILP solver (primary choice for DoD Nexus)

library(ROI)            				# R Optimization Infrastructure

library(Rglpk)          				# GNU Linear Programming Kit interface

library(ompr)           				# Optimization Modeling Package for R

library(ompr.roi)       				# ROI solver interface for ompr

Data Manipulation and Processing

```r

# Core data manipulation

library(dplyr)          				# Data transformation and manipulation

library(tidyr)          				# Data reshaping and tidying

library(data.table)     				# High-performance data operations for large datasets

library(purrr)          				# Functional programming tools

# Data import/export

library(readxl)         				# Excel file reading

library(openxlsx)       				# Excel file writing and formatting

library(readr)          				# Fast CSV reading/writing

library(haven)          				# SAS file import (for transition period)

Graph Analysis and Clustering

```r

# Network analysis for LIN clustering

library(igraph)         				# Graph algorithms and connected components

library(cluster)        				# Additional clustering algorithms

library(Matrix)         				# Sparse matrix operations

Advanced Optimization (Enhanced Features)

```r

# Multi-objective optimization

library(mco)            				# Multi-criteria optimization

library(nsga2R)         				# Non-dominated Sorting Genetic Algorithm II

# Stochastic programming

library(ROI.plugin.symphony)  		# Symphony solver for larger problems

library(DEoptim)        				# Differential Evolution optimization

Statistical and Mathematical Libraries

```r

# Statistical functions

library(stats)          				# Built-in statistical functions

library(MASS)           				# Additional statistical functions

# Mathematical operations

library(pracma)         				# Practical numerical math functions

Reporting and Visualization

```r

# Report generation

library(rmarkdown)      # Dynamic report generation

library(knitr)          # Document generation

library(DT)             # Interactive data tables

# Visualization

library(ggplot2)        # Grammar of graphics plotting

library(plotly)         # Interactive plots

library(gridExtra)      # Multiple plot arrangements

Interactive Dashboard Development

```r

# Web applications

library(shiny)          # Interactive web applications

library(shinydashboard) # Dashboard framework

library(shinyWidgets)   # Enhanced UI widgets

library(htmltools)      # HTML generation tools

Utility and Support Libraries

```r

# String manipulation

library(stringr)        # String operations

library(glue)           # String interpolation

# Date/time operations

library(lubridate)      # Date and time manipulation

# Configuration and logging

library(config)         # Configuration management

library(logging)        # Logging framework

library(yaml)           # YAML configuration files

# Testing framework

library(testthat)       # Unit testing

library(assertthat)     # Assertions and validation

Performance and Memory Management

```r

# Performance monitoring

library(pryr)           # Memory usage monitoring

library(microbenchmark) # Performance benchmarking

library(parallel)       # Parallel processing

library(foreach)        # Parallel loops

library(doParallel)     # Parallel backend

Specialized Military/Government Libraries

```r

# Note: These may need to be developed internally if not available in DoD Nexus

# OR use generic equivalents with custom wrapper functions

library(scales)         # Scaling functions for formatting

Priority Installation Order

Phase 1: Essential Core (Week 1)

```r

# Must-have for basic functionality

c("lpSolve", "dplyr", "data.table", "readxl", "openxlsx",

"igraph", "ROI", "stringr", "lubridate")

Phase 2: Standard Operations (Week 2)

```r

# Required for full basic system

c("tidyr", "purrr", "readr", "cluster", "Matrix", "stats",

"MASS", "ggplot2", "rmarkdown", "knitr", "testthat")

Phase 3: Enhanced Features (Week 3+)

```r

# Advanced capabilities

c("mco", "DEoptim", "shiny", "shinydashboard", "plotly",

"DT", "parallel", "foreach", "doParallel", "config", "yaml")

DoD Nexus & ARC/cProbe Compatibility Notes

** All libraries available in ARC/cProbe RStudio Pro Environment **

High Probability Available

- All `tidyverse` packages (dplyr, tidyr, ggplot2, readr, stringr, lubridate, purrr)

- Base optimization (lpSolve, ROI)

- Standard R packages (stats, MASS, cluster, Matrix)

- Reporting (rmarkdown, knitr)

Medium Probability Available

- Specialized optimization (ompr, mco)

- Advanced visualization (plotly, shiny)

- Excel integration (readxl, openxlsx)

May Need Approval/Alternatives

- Performance monitoring (pryr, microbenchmark)

- Advanced solvers (ROI.plugin.symphony)

- Web frameworks (shinydashboard, shinyWidgets)

Fallback Strategies

If Advanced Packages Unavailable

```r

# Use base R equivalents

base::optimize()        # Instead of advanced optimizers

utils::read.csv()       # Instead of readr

base::apply()           # Instead of purrr functions

grDevices::pdf()        # Instead of advanced plotting

Custom Development Requirements

If certain packages aren't available in DoD Nexus, we may need to develop:

- Custom Excel interface using base R

- Simple logging framework

- Basic optimization wrapper functions

Total Package Count

- Essential Core: 9 packages

- Standard Operations: 11 packages

- Enhanced Features: 12 packages

- Total Maximum: ~32 packages

This dependency list is designed to be modular - the system can function with just the essential core packages and progressively add capabilities as more packages become available in the DoD environment.

Configuration Files

# config/parameters_gtw.yaml

optimization:

use_substitutions: true

p_pri: 10000000000

a_pri: 500

trans_pen: 150

mod_5_e_pen: 999

sub_assign_pen: 0.01

data_sources:

current_fy: 2025

max_date: 2031

fill_target: 1.0

Testing Strategy Details

Unit Testing Implementation

# Example: test_data_processing.R

test_that("SACS processing maintains requirement totals", {

# Load test data

test_sacs <load_test_sacs_data()

# Process data

result <process_sacs(test_sacs)

# Validate totals

original_total <sum(test_sacs$RQEQP, na.rm = TRUE)

processed_total <sum(result$req, na.rm = TRUE)

expect_equal(original_total, processed_total, tolerance = 0.01)

})

test_that("MILP optimization satisfies all constraints", {

# Create simple test problem

test_problem <create_test_optimization_problem()

# Solve

solution <solve_milp(test_problem)

# Validate constraint satisfaction

expect_true(validate_inventory_constraints(solution))

expect_true(validate_requirement_constraints(solution))

})

Integration Testing Framework

# test_integration.R

test_that("End-to-end GTW scenario produces valid results", {

# Full pipeline test

config <load_config("gtw")

# Run complete pipeline

results <run_ngrer_optimization(

scenario = "GTW",

config = config,

test_mode = TRUE

)

# Validate outputs

expect_s3_class(results, "ngrer_results")

expect_true(all(results$assignments >= 0))

expect_equal(

sum(results$requirements),

sum(results$assignments) + sum(results$shortages)

)

})

Performance Benchmarks and Monitoring

Performance Targets

| Dataset Size | Processing Time | Memory Usage | Success Criteria |
| --- | --- | --- | --- |
| Small (100 LINs, 50 units) | <5 minutes | <2GB | 100% constraint satisfaction |
| Medium (1,000 LINs, 500 units) | <30 minutes | <8GB | >99% optimal solutions |
| Full (2,500+ LINs, 2,000+ units) | <4 hours | <16GB | >95% solutions within 5% gap |

Memory Management Strategy

# R/utilities/memory_management.R

monitor_memory_usage <function() {

current_usage <pryr::mem_used()

max_usage <memory.size(max = TRUE)

if (current_usage > 0.8 * max_usage) {

warning("Memory usage approaching limit: ",

round(current_usage/1024^3, 2), "GB")

gc(verbose = TRUE)

}

}

process_large_dataset_chunked <function(data, chunk_size = 10000) {

results <list()

n_chunks <ceiling(nrow(data) / chunk_size)

for (i in 1:n_chunks) {

start_idx <(i 1) * chunk_size + 1

end_idx <min(i * chunk_size, nrow(data))

chunk_result <process_chunk(data[start_idx:end_idx, ])

results[[i]] <chunk_result

# Memory cleanup

if (i %% 5 == 0) gc()

}

return(do.call(rbind, results))

}

Risk Mitigation and Validation Protocol

Data Validation Framework

# R/utilities/data_validation.R

validate_sacs_data <function(sacs_data) {

checks <list(

uic_format = all(nchar(sacs_data$UIC) == 6),

lin_format = all(nchar(sacs_data$LIN) == 6),

positive_quantities = all(sacs_data$RQEQP >= 0, na.rm = TRUE),

valid_components = all(sacs_data$COMPO %in% c("1", "2", "3", "6")),

no_missing_critical = !any(is.na(sacs_data[c("UIC", "LIN", "COMPO")]))

)

failed_checks <names(checks)[!unlist(checks)]

if (length(failed_checks) > 0) {

stop("Data validation failed: ", paste(failed_checks, collapse = ", "))

}

return(TRUE)

}

validate_optimization_results <function(results) {

# Check mathematical consistency

assignments_valid <all(results$assignments >= 0)

# Check requirement satisfaction

total_allocated <results$assignments + results$substitutions + results$transfers

requirements_met <abs(total_allocated + results$shortages results$requirements) < 1e-6

# Check inventory conservation

inventory_conserved <sum(results$initial_inventory) >=

sum(results$assignments) + sum(results$transfers_out)

validation_results <list(

assignments_valid = assignments_valid,

requirements_met = all(requirements_met),

inventory_conserved = inventory_conserved,

solution_feasible = all(c(assignments_valid, all(requirements_met), inventory_conserved))

)

return(validation_results)

}

Parallel Development Strategy

# Run both systems during transition

compare_sas_r_results <function(sas_results, r_results, tolerance = 0.05) {

# Standardize data formats

sas_std <standardize_sas_output(sas_results)

r_std <standardize_r_output(r_results)

# Compare key metrics

comparisons <list(

total_assignments = compare_totals(sas_std$assignments, r_std$assignments),

total_shortages = compare_totals(sas_std$shortages, r_std$shortages),

total_transfers = compare_totals(sas_std$transfers, r_std$transfers),

eoh_by_component = compare_by_component(sas_std$eoh, r_std$eoh)

)

# Generate discrepancy report

discrepancies <lapply(comparisons, function(x) {

abs(x$difference) > tolerance

})

return(list(

comparisons = comparisons,

discrepancies = discrepancies,

overall_match = !any(unlist(discrepancies))

))

}

Deployment and Transition Plan

Phase 1: Proof of Concept (Weeks 19-20)

- Deploy single-component test version

- Run parallel with existing SAS system

- Validate results against historical data

- Performance benchmarking

Phase 2: Pilot Deployment (Weeks 21-22)

- Deploy full R system with selected components

- Train analysts on new system interface

- Document any issues and performance gaps

- Refine based on user feedback

Phase 3: Full Production (Weeks 23-24)

- Complete system deployment

- Knowledge transfer completion

- SAS system retirement planning

- Documentation finalization

Success Criteria

- Accuracy: <1% difference in total equipment assignments compared to SAS

- Performance: Complete NGRER cycle processing within 4-hour window

- Reliability: 99% successful completion rate over 10 test runs

- Usability: Analysts can complete standard analysis tasks within 2 hours

- Maintainability: New requirements implementable within 2-week sprints

Rollback Plan

- Maintain SAS system in parallel for first 3 months

- Documented procedure for reverting to SAS if critical issues arise

- Data backup and recovery procedures

- 24-hour notification protocol for system issues

This comprehensive plan provides the roadmap for migrating the NGRER optimization system from SAS to R while maintaining analytical capability and meeting all statutory reporting requirements.